## Master Action Plan
MASTER ACTION PLAN — All Open Work Items
Consolidated from: MASTER-PLAN, ACTION-TRACKER, 7 gameplans, CC Action Items (100 items) ¦ Generated: April 11, 2026 ¦ 79 unique items
Domain | Action Item | Owner | Effort | Priority | Status | Source | Notes
Infrastructure
Infrastructure | Rotate exposed API keys (GitHub PAT + Voyage AI) | Kiran | S | Critical | Blocked | PLATFORM-MIGRATION | Keys captured in session archives. GitHub Settings → Developer Settings → PATs.
Infrastructure | Rotate LinkedIn client secret | Kiran | S | Critical | Blocked | Session 5 | Scrubbed with [REDACTED]. LinkedIn Developer Portal → Supabase Dashboard.
Infrastructure | Obtain written consent from Feeding America + Best Friends | Kiran | M | Critical | Blocked | SCANNIBAL / DIA-FUND | Blocks paid tier launch, App Store submission. Emails sent Mar 17.
Fenix
Fenix | ping_kiran decision: keep (Resend vs Pushover) or revert | Kiran | S | High | Parked | Session 4-5 | Built without gates in S4. Reverted in S5. Needs proper decision.
Fenix | Blog post personalization — 4 sections need Kiran's voice | Kiran | M | High | Todo | Session 6 | fenix-how-it-works.md in WordWeaver fbb30a84. Portfolio story, debugging anecdote, tech depth, philosophy.
Fenix | Test 6 model-side improvement (connect_visitor ~15% flake) | Claude | M | Medium | Parked | Session 6 | Server-side catches 100%. Nice-to-have to reduce model attempts.
Fenix | Build booking_meeting tool (Phase 2) | Claude | XL | Medium | Parked | FENIX-AI-ROADMAP | Calendly integration. Requires Cal.com setup (Kiran task).
Fenix | Build send_summary tool (Phase 2) | Claude | XL | Medium | Parked | FENIX-AI-ROADMAP | Email follow-up with conversation highlights.
Fenix | Conversation persistence to Supabase | Claude | L | Medium | Parked | FENIX-AI-ROADMAP | Currently SessionStorage only. Phase 2 item.
Fenix | Build run_fit_score tool (Phase 3) | Claude | XL | Low | Parked | FENIX-AI-ROADMAP | JD evaluation with visible thinking. Needs connected visitor.
Fenix | Build generate_micro_teardown tool (Phase 3) | Claude | XL | Low | Parked | FENIX-AI-ROADMAP | On-demand product analysis. Phase 3 showcase.
Fenix | Voice mode (Phase 4) | Joint | XL | Low | Parked | FENIX-AI-ROADMAP | ElevenLabs integration. Phase 4.
Fenix | Dynamic page personalization (Phase 4) | Claude | XL | Low | Parked | FENIX-AI-ROADMAP | Adapt site experience based on conversation signals.
Fenix | Test agentic Fenix tool use on mobile | Kiran | S | Medium | Todo | CC Action Items | Mobile responsiveness check for tool interactions.
Fenix | Implement dynamic frontend state-driven pills (Option C) | Claude | L | Medium | Parked | CC Action Items | Frontend pill generation based on state, not just backend.
Fenix | Build Fenix training dashboard frontend | Claude | L | Medium | Parked | MASTER-PLAN B8 | 8 analytics endpoints exist. Frontend NOT built.
Fenix Training
Fenix Training | Author 5 recruiter question answers | Kiran | M | High | Todo | MASTER-PLAN K1 | HOMEWORK-Recruiter-Questions.md. Blocks evaluator unlocks + Fenix knowledge.
Fenix Training | Do 2-3 Fenix training sessions (~10-15 Q&As each) | Kiran | L | High | Todo | MASTER-PLAN K2 | 319-question bank, ~80-100 approved. 220 unanswered across 5 personas.
Fenix Training | Focus on thin dimensions (fun, opinions, personal) | Kiran | M | Medium | Todo | MASTER-PLAN D7 | RAG coverage gaps in non-professional dimensions.
Homepage
Homepage | Work card strategy (D3) | Joint | L | High | Todo | HOMEPAGE-GAMEPLAN | Highest priority remaining homepage item.
Homepage | Set up Cal.com account and booking page | Kiran | S | High | Todo | CC Action Items | Blocks Connect section. Two event types: intro call + pairing session.
Homepage | Design Connect contact flow | Joint | L | High | Todo | CC Action Items | Progressive engagement system. Currently static button.
Homepage | Fix force graph rendering bug in proto-combined.html | Claude | M | High | Done | CC Action Items | Session 7: Fixed hardcoded 700px height fallback in skills.html.
Homepage | Finalize learning page prototype → replace learning.html | Claude | M | High | Done | CC Action Items | Done — learning.html correctly redirects to /skills. skills.html IS the learning page (D3.js interactive viz). Session 7b.
Homepage | Wire up resume PDF downloads for three lenses | Joint | L | High | Todo | CC Action Items | Needs Kiran's resume content for 3 lens variants.
Homepage | Fix panel swapping — panels must update on latest interaction | Claude | M | High | Done | CC Action Items | Session 7: Fixed state sync — fenixState set before showPanel() call.
Homepage | Hero video — why this site exists | Kiran | L | High | Todo | CC Action Items | Foundational gap. MJ portrait → HeyGen → CapCut.
Homepage | Full visual consistency audit | Claude | L | Medium | Done | CC Action Items | Done — Full audit of 10 pages against VISUAL-STANDARDS.md. Report at docs/VISUAL-AUDIT-REPORT.md. Session 7b.
Homepage | Em-dash sweep across 6 flagged files | Claude | S | Medium | Done | CC Action Items | Session 7: 60 replacements across 6 files. Committed.
Homepage | Rewrite testimonials page copy + fix missing nav | Claude | M | Medium | Done | CC Action Items | Session 7: Nav updated to 10 items matching main site. Fix:13a/13b resolved.
Homepage | Rewrite first Fenix welcome message | Joint | S | Medium | Todo | CC Action Items | Warmer, guide-oriented.
Homepage | Add typing animation for Fenix welcome | Claude | S | Medium | Done | CC Action Items | Session 7: IntersectionObserver + 30ms/char typing with blinking cursor.
Bento Cards
Bento Cards | Generate 14 MJ images for desktop bento grid | Kiran | L | High | Todo | BENTO-CARD-GAMEPLAN | Priority 1: 4 images covering 8+ persona slots.
Bento Cards | Update V5 scene prompt dimensions for bento-shapes layout | Claude | M | High | Done | CC Action Items | Done — V6 doc already has correct full-card aspect ratios. No changes needed. Session 7b.
Bento Cards | Generate remaining 8 monster character scenes (MJ) | Kiran | L | High | Todo | CC Action Items | Only Veteran.png exists. 8 more needed.
Bento Cards | Integrate MJ images into imageMap + test all personas | Claude | M | Medium | Parked | MASTER-PLAN B3 | Blocked on Kiran generating art.
Track Record
Track Record | Phase 1: Strategic angle review (leadership, impact, arrows) | Joint | L | High | Todo | TR-V5-TRIMMING | Bias pressure tests + 5 strategic angles.
Track Record | Phase 2: Trim 26 pairs → 16-18 pairs | Joint | L | High | Todo | TR-V5-TRIMMING | Based on bias checks and metric strength.
Track Record | Phase 3: Polish (animations, synthesis, world events) | Claude | L | Medium | Todo | TR-V5-TRIMMING | After trim is done.
Track Record | Get Eagle Invest metrics from former colleagues | Kiran | M | High | Todo | CC Action Items | Social proof data.
Persona Picker
Persona Picker | Deep dive: Evaluator (Merritt) persona unlock design | Joint | XL | High | Todo | PERSONA-PLAYBOOK | Track 1 (visual) + Track 2 (functional).
Persona Picker | Design Fit Score mechanics | Joint | L | High | Todo | CC Action Items | Scoring dimensions, weighting, reverse evaluation.
Persona Picker | Build full production Evaluator experience | Claude | XL | High | Todo | CC Action Items | After design is locked.
Persona Picker | Confirm constraint framework — 3 per persona max | Kiran | S | High | Todo | CC Action Items | Prioritization test.
Persona Picker | Pick evaluator game format (A/B/C) | Kiran | M | High | Todo | MASTER-PLAN D1 | Spot the Red Flag vs Would You Hire vs Anti-Interview.
Persona Picker | Author 5-7 game scenarios/questions | Kiran | L | High | Todo | MASTER-PLAN K3 | After format is picked.
Persona Picker | Build second persona adapter (Seeker or Practitioner) | Claude | XL | Medium | Parked | MASTER-PLAN C1 | Phase C. Kiran picks which persona.
Persona Picker | Build remaining 4 persona adapters | Claude | XL | Low | Parked | MASTER-PLAN C2 | Phase C. ~1 session each.
Persona Picker | Prototype unlock component visual format | Joint | M | Medium | Parked | CC Action Items | Cards vs text vs menu.
Content
Content | Create content for 3 new work cards (Under the Hood, Frameworks, /Now) | Kiran | L | High | Todo | CC Action Items | Content doesn't exist yet.
Content | Choose first teardown target company | Kiran | M | High | Todo | CC Action Items | GTM Tier 1 distribution engine test.
Content | Add honesty markers to 5 flagged blog posts | Joint | M | Medium | Todo | CC Action Items | Reclassified: needs Kiran's voice — dead ends, surprises, personal anecdotes.
Content | Write hero video script (4-beat narrative) | Kiran | M | High | Todo | CC Action Items
Content | Soft launch messaging — how to introduce site | Kiran | M | High | Todo | CC Action Items | For friendly recruiters.
Content | Under the Hood: voice pass on v1 draft | Kiran | M | Medium | Todo | CC Action Items | Especially Product Strategy section.
Content | Under the Hood: create visual artifacts | Joint | M | Medium | Todo | CC Action Items | Excalidraw diagrams, CC screenshots.
Command Center
Command Center | Build CC API endpoint for site OUTCOMES metrics | Claude | L | High | Done | CC Action Items | Done — GET /api/fenix/outcomes endpoint added. Aggregates conversations, visitors, connections, fit scores, navigation. Session 7b.
Command Center | Build Add Skills feature | Claude | L | High | Done | CC Action Items | Done — Feature already exists: 5-tab React component at add-skills/page.tsx with full backend (evidence_service). Session 7b.
Command Center | Career Initiatives entity (CRUD, migration, RAG) | Claude | L | Medium | Done | CAREER-INITIATIVES-CC | Done — Full CRUD API, 32 initiatives migrated from career-highlights.html, domain/company filtering. Session 7b.
Command Center | Fix CC conversation detail — show Fenix responses | Claude | M | Medium | Done | CC Action Items | Session 7: store_message was async with no await — messages never persisted. Fixed.
Command Center | Plug evidence update into MadLab publish pipeline | Claude | M | Medium | Done | CC Action Items | Session 7: Added generate_manifest() call after create_source().
Command Center | Plug evidence update into teardown publish pipeline | Claude | M | Medium | Done | CC Action Items | Session 7: Added generate_manifest() call after create_source().
Command Center | Build CC notification service (Pushover) | Claude | L | Medium | Parked | MASTER-PLAN C5 | Needs $5 Pushover purchase.
Command Center | Provide subscription costs for Cost Monitor | Kiran | S | Medium | Todo | CC Action Items
Career
Career | Map warm network against 9 target companies | Kiran | L | High | Todo | CC Action Items | LinkedIn 1st/2nd degree connections. Highest-ROI GTM.
Career | Technical upskilling Phase 1 (weeks 1-4) | Kiran | XL | High | Todo | CC Action Items | Solidify existing skills.
Career | Technical upskilling Phase 2 (weeks 5-8) | Kiran | XL | High | Todo | CC Action Items | AI prototyping fluency.
Career | Technical upskilling Phase 3 (weeks 9-12) | Kiran | XL | High | Todo | CC Action Items | System design credibility.
Career | Review strategy docs (SITE-WHY, ULTIMATE-PERSONA, GO-TO-MARKET) | Kiran | M | High | Todo | CC Action Items | Reference docs for all future sessions.
Career | Create resume lens variants (AI PM, Growth, Product Strategy) | Joint | L | Medium | Todo | CC Action Items
Career | Define technical skills that matter most for PM hiring in 2026 | Kiran | M | Medium | Todo | CC Action Items
Infrastructure
Infrastructure | Register LinkedIn OAuth developer application | Kiran | S | Medium | Todo | CC Action Items | Blocks LinkedIn sign-in path.
Infrastructure | Purchase Pushover license ($5) | Kiran | XS | Low | Todo | MASTER-PLAN K8 | Blocks notification service.
Infrastructure | Delete prototype files from repo | Claude | S | Medium | Done | CC Action Items | Session 7: Removed 47 files (prototypes, backups, stale artifacts). Committed.
Infrastructure | Structured logging + error tracking | Claude | L | Medium | Parked | ARCHITECTURE debt | Delta to World Class item.
Creative
Creative | Audit Studio creative content — what actually exists? | Kiran | M | High | Todo | CC Action Items | AI songs, photography, custom fonts. Studio card depends on this.
Creative | Animate hero image via Runway Gen-4 | Kiran | M | High | Todo | MASTER-PLAN K5 | Coffee steam + sleeping dog cinemagraph.
Creative | Produce manifesto video (MJ → HeyGen → CapCut) | Kiran | L | Medium | Todo | MASTER-PLAN K6 | 60s, 5 scenes. ~$98 production cost.
Creative | Select AI avatar tool for hero video | Kiran | S | Medium | Todo | CC Action Items

## Summary
Action Plan Summary
By Owner
Kiran | 35
Claude | 31
Joint | 13
By Priority
Critical | 3
High | 37
Medium | 33
Low | 6
By Status
Todo | 44
Blocked | 3
Parked | 17
Done | 15
By Domain
Fenix | 13
Homepage | 13
Persona Picker | 9
Command Center | 8
Infrastructure | 7
Content | 7
Career | 7
Bento Cards | 4
Track Record | 4
Creative | 4
Fenix Training | 3
Session 7b (Apr 12, 2026)
6 Claude items completed: career-initiatives entity, outcomes endpoint,
learning page, bento dimensions, visual audit, add-skills confirmation